## KT Plan for Sai
Topic | Sub-Topic | Taken By | Duration in Hrs | Date | Comments | Status
1. What is Springboard |  | Snehal | 30 Min | 2nd Nov |  | Done
2. Highlevel Architecture of Springboard |  | Snehal | 40 Mins | 3rd Nov
3. Springboard Codebase
4. SpringBoard Modules like | fundraiser modules | Snehal | 45 Mins | 6th Nov
| Springboard Users | Snehal
| Spring Cleaning | Snehal
| Springboard Fraud | Snehal
| Springboard Webforms | Pratap | 30 Min | 03rd Nov
| Email Wrappers | Pratap | 30 Min | 06th Nov
| Page Wrappers | Pratap | 30 Min | 07th Nov
| Webform Users | Pratap | 30 Min | 15th Nov
| Webform Confirmations | Pratap | 30 Min | 16th Nov
| Springboard Admin | Pratap | 30 Min | 17th Nov
| Salesforce | Pratap | 30 Min | 20th Nov
| Springboard Views | Pratap | 30 Min | 21stNov
5. Springboard Profiles
6. Springboard Themes
7. Cronjob Functionality | How to implement cron and how to execute it | Snehal | 30 Mins | 7th Nov
8. GitLab Project related knowledge and deployment process |  | Snehal | 45 Mins | 9th Nov
9. Jira knowledge
10. Coding Standard Knowledge