## Summary
Summary
Consolidated Effort Distribution
Requirements | 1
Design | 0
Coding and Unit Testing | 30
FET | 11
Testing and Delivery | 15
General | 0
Total | 57
Effort Estimate in person days | #VALUE!
Total Efforts in persondays | #VALUE!
Project Management Efforts in person days | #VALUE!
Grand Total in person days | #VALUE!
Grand Total in person months | #VALUE!
Estimated Total person months split resource wise
UI Designers | #VALUE!
Technical Writers | #VALUE!
Developers | #VALUE!
QA Engineers | #VALUE!
Project Managers | #VALUE!
Total | #VALUE!
Cost Estimate
Rate
UI Designers
Technical Writers
Developers
QA Engineers
Project Managers
Total Cost
UI Design | #VALUE!
User Documentation | #VALUE!
(Development + QA) | #VALUE!
Project Management | #VALUE!
Grand Total Cost | #VALUE!
Note on D17: This is done to calculate estimated cost separately as rates are different
Note on E23: Check if this is same as E16 (Grand Total in person months)

## TMS Website Estimation
Task Based Estimation
Project ID |  | Domain |  | EnterpriseContentManagement
Project Name | TMS (https://tmssiteprod.prod.acquia-sites.com/) | Current Project Phase |  | Requirement (CMS - Drupal)
Version | 1
All the estimations are in persondays unless and otherwise specified.
Estimation of Requirements |  | Complexity | Development | [5 empty] | TOTAL
Sr. No. | Task/ Feature Description |  | Feasibility Study | Requirements (Req. Mgmt & Review) | Design (Design &Review) | Construction (Coding, Review & Unit Testing) | FET | Testing (ST+UAT) |  | Comments/Assumptions
| Project Architecture and Modularization | [9 empty] | Average complexity
1 | Requirement understanding/SRS preparation | 3 |  | 1 |  |  |  |  | 1
2 | Information Architecture | 3 |  |  |  | 1 |  |  | 1
Discovery
3 | Auditing website performance and suggesting the performance improvement plan | 3 | 1 | [5 empty] | 1
4 | Auditing website security, anti-spam & caching tools and suggesting corrective actions | 3 | 1 | [5 empty] | 1
5 | Auditing SEO and provide recommendations | 3 | 1 | [5 empty] | 1
6 | Auditing Drupal core, Database, hosting environment & modules used and identifying the outdated/un-supported code/modules | 3 | 1 | [5 empty] | 1
Core Web Vitals: Desktop & Mobile
7 | Better user experience by improving the website performance & keeping site optimized: | 3 | [6 empty] | 0
| Upgrading the site to the latest version of Drupal 9.5.9 with upgrade all modules to their stable versions and remove/replace any unsupported modules. | 3 |  |  |  | 2 |  |  | 2
| Updating the PHP version to 8.1 and addressing any issues found in the error log and status report page. This will involve updating any custom modules, applying contributed module patches, and, in some cases, creating custom patches to resolve any issues | 3 |  |  |  | 3 |  |  | 3
| Implementing Memcache and Varnish caching solutions (website caching) | 3 |  |  |  | 2 |  |  | 2
| Cron setup and configuration | 3 |  |  |  | 1 |  |  | 1
| Implementing CDN | 3 |  |  |  | 1 |  |  | 1
| Images optimization & alt attribute implementation | 3 | 1 |  |  | 1 |  |  | 2
| To improve performance lots of factors need to be checked and taken care of. Minify CSS and JS, Performance-oriented Drupal theme changes, Use Drupal modules like AdvAgg and others and Optimize server performance | 3 | 1 |  |  | 1 |  |  | 2
| Visit each and every page to find existing issues and fix them including mobile performance improvement | 3 |  |  |  | 3 |  |  | 3
| Fix administration theme-related issues. Two options: | 3 | [6 empty] | 0
| 1. Fix existing issues in the current theme. | 3 |  |  |  | 2 |  |  | 2
| 2. Use a different admin theme. | 3 |  |  |  | 1 |  |  | 1
| Fixing the security issues and existing bugs | 3 |  |  |  | 1 |  |  | 1
| Include module and make configuration changes to boost website's SEO | 3 |  |  |  | 2 |  |  | 2
| Accessibility — the Priority level 1 errors noted on tab "01-08" attached need to be addressed for launch. Keyboard issues are critical and need to be resolved. | 3 |  |  |  | 4 |  |  | 4
| Fixing the security issues and existing bugs | 3 |  |  |  | 1 |  |  | 1
Integration and UAT
8 | Build and deployment | 3 |  |  |  | 1 |  |  | 1
9 | UAT/Stabilization | 3 |  |  |  | 2 |  |  | 2
10 | Production Deployment | 3 |  |  |  | 1 |  |  | 1
FET
11 | FET | 3 |  |  |  |  | 11 |  | 11
QA/Testing
12 | QA/Testing | 3 | [5 empty] | 15 | 15
Total |  | 3 | 6 | 1 | 0 | 30 | 11 | 15 | 63
General
1 | User Interface (UI) work | 5
2 | Rework (Defect-fixing)
3 | Defect Verification
4 | Build, Release & Deployment
5 | Client Communication
6 | User Documentation
7 | Client Training | 0.5
| Total | 5.5
A | Out of Scope
1 | UI/UX changes in website
2 | CI/CD integrations
3 | Content creation
4 | Multilingual / Multi Domain / Multi Site website feature
5 | User training
6 | AD, SSO & LDAP Integration
7 | Development of Mobile App
8 | Social media integration like FB, Instagram etc.
9 | CRM Integrations
B | Assumptions
1 | Estimates are high level and to be re-estimated in case of change in requirements/understanding/assumptions
2 | Website is developed in Drupal and hosted on Acquia cloud
3 | Client to Acquia cloud environment details
4 | Client to share drupal admin Backend and codebase access
5 | Client to share the details of any third party APIs integration
6 | The application is going to support the latest 4 browsers (chrome, Mozilla, safari and Edge) and 2 iOS and Android device
7 | UI/UX changes to be estimated separately
8 | QA testing is restricted to manual only
Note on A6: While estimating consider the following points in mind: - Technical complexity - Domain knowledge - Third party software dependency - Complexity of the software - Scalability of the Software - Security of software - Reusability of Software - Analyst and programmer capability - Experience of team in the application area - Experience of team with the programming language and computer - Use of tools and software engineering practices - Experience of team on Testing Software
Note on B46: Rework would follow review/ testing. Generally, rework efforts are estimated at 5-7% of total efforts
Note on B48: (Based on no. of builds)
Note on D7: Feasibility Study (FS) Time taken for Feasibility Study. This is applicable only if there is a feasibility study of the project is required Else enter the value 0 Estimates need to be put in the persondays .
Note on E7: Requirements Management (RM) following are the efforts should be considered while estimating for thr requirements: - Generation of the work product like SRS, RUD etc. - Rework effort - Verification effort i.e. time for requirements review - Planning and orientation effort Estimates need to be put in the persondays i.e. 2 personhours= .25 persondays 4 personhours= .5 persondays 8 personhours= 1 persondays
Note on F7: Design: following are the efforts should be considered while estimating for thr requirements: - Generation of the work product like HLD, LLD etc. - Rework effort - Verification effort i.e. time for Design review - Planning and orientation effort Estimates need to be put in the persondays i.e. 2 personhours= .25 persondays 4 personhours= .5 persondays 8 personhours= 1 persondays
Note on G7: Coding: following are the efforts should be considered while estimating for thr requirements: - Generation of the work product (code) - Rework effort - Verification effort i.e. time for code review - Planning and orientation effort Estimates need to be put in the persondays i.e. 2 personhours= .25 persondays 4 personhours= .5 persondays 8 personhours= 1 persondays
Note on I7: Testing: Following are the efforts should be considered while estimating for thr requirements: - Generation of the work product like writing test cases (SI, UAT etc) and executing test cases. - Rework effort - Verification effort i.e. time for test case review - Planning and orientation effort Estimates need to be put in the persondays i.e. 2 personhours= .25 persondays 4 personhours= .5 persondays 8 personhours= 1 persondays

## Resource Loading
Resource Loading
| Requirement Understanding/Design | Development |  |  |  | Testing | Deployment | Total person Days
| Week-1 | Week-2 | Week-3 | Week-4 | Week-5 | Week-6 | Week-7
FET |  |  | 1 | 1 | 1 |  |  | 15
Technical Writers | [7 empty] | 0
Drupal Developers | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 35
QA Engineers |  |  |  |  | 1 | 1 | 1 | 15
Project Managers | [7 empty] | 0
Days in Week | 5 | 5 | 5 | 5 | 5 | 5 | 5
Efforts in a Persons day | 5 | 5 | 10 | 10 | 15 | 10 | 10 | 65
Note on I12: This plan is tentative, but most realistic judgement of estimators as of now. Effort should be same as the effort in TBE sheet

## New SOW Estimation
Task Based Estimation
Project ID |  | Domain |  | EnterpriseContentManagement
Project Name | TMS (https://www.tmsw.com/) | Current Project Phase |  | Requirement (CMS - Drupal)
Version | 2
All the estimations are in persondays unless and otherwise specified.
Estimation of Requirements |  | Complexity | Development | [5 empty] | TOTAL
Sr. No. | Task/ Feature Description |  | Feasibility Study | Requirements (Req. Mgmt & Review) | Design (Design &Review) | Construction (Coding, Review & Unit Testing) | FET | Testing (ST+UAT) |  | Comments/Assumptions
SOW 1: Priority - Core Web Vitals (Desktop & Mobile)
1 | Translations — turning on the LanguageWire integration so we can implement French translations across the website | 3 |  |  |  | 4 |  |  | 4
2 | Make prod preview links viewable (but not publicly published) even if a user does not have a CMS login — we need to be able to internally share links with our teams/colleagues for review and at the moment we cannot do this, as the prod links for unpublished content can only be viewed via a CMS login | 3 | [6 empty] | 0 | Out of scope of Drupal. Need some more time to dig into this and to check if Drupal does allow to perform this integration.
3 | Change video settings so we can link to any hosted video, not just via Vimeo | 3 |  |  |  | 5 |  |  | 5
4 | Hosting PDF pages — as mentioned in JIRA, this is needed so we can host PDFs for an event but also to resolve a policy page issue | 3 |  |  |  | 6 |  |  | 6
5 | Hosting gated content (white paper) | 3 | [6 empty] | 0 | Need some time for researching about this implementation. Not sure if we can handle this from Drupal CMS side or Acquia server side.
6 | SEO — potential workload for Cybage to assist in fixing the following SEO components: 1. Metadata – heading structures, descriptions, title tags, URL correcting 2. Site Performance – compressing media files, mobile usability 3. Backlinking correction | 2 |  |  |  | 4 |  |  | 4
SOW 2: Priority - Core Web Vitals (Desktop & Mobile)
7 | Add caption option on videos — we’d like to be able to add a sentence or two that explains what the video is about just below where the video shows on the page. This should be a feature we can toggle on or off and should be editable in the CMS, not hard coded. | 3 |  |  |  | 4 |  |  | 4
8 | Change homepage split image to video — the image in the green section of the homepage (titles in the section are “Careers” and “Locations”) should be switch to a video (tms can provide the file) and not hard-coded | 3 |  |  |  | 4 |  |  | 4
9 | Homepage content selection — selection process for curating content on the homepage is clunky. Currently you have to go to Structure > Manage Site Settings > Homepage Trending Sort or Latest Work Sort. Can this be improved so that the homepage content defaults to the post recent blog or case study published but then we can still override it if needed? | 3 |  |  |  | 4 |  |  | 4
10 | Work overview page order — not sure if this is related to point above, case study work order on the work page isn’t automatically in order of what’s shared most recently. Ideally we’d resolve so most recent work shows at the top. | 2 |  |  |  | 4 |  |  | 4
11 | Ability to update our individual passwords in CMS — currently we can do change the pass in the CMS, but it reverts to the original pass and doesn’t let us use the new credentials. This seems like a security risk. | 3 |  |  |  | 4 |  |  | 4
Integration and UAT
8 | Build and deployment | 3 |  |  |  | 1 |  |  | 1
9 | UAT/Stabilization | 3 |  |  |  | 2 |  |  | 2
10 | Production Deployment | 3 |  |  |  | 1 |  |  | 1
FET
11 | FET | 3 |  |  |  |  | 15 |  | 15
QA/Testing
12 | QA/Testing | 3 | [5 empty] | 10 | 10
Total |  | 2.875 | 0 | 0 | 0 | 43 | 15 | 10 | 68
General
1 | User Interface (UI) work | 5
2 | Rework (Defect-fixing)
3 | Defect Verification
4 | Build, Release & Deployment
5 | Client Communication
6 | User Documentation
7 | Client Training | 0.5
| Total | 5.5
A | Out of Scope
1 | Make prod preview links viewable (but not publicly published) even if a user does not have a CMS login — we need to be able to internally share links with our teams/colleagues for review and at the moment we cannot do this, as the prod links for unpublished content can only be viewed via a CMS login
2 | AD, SSO & LDAP Integration
3 | Development of Mobile App
4 | Social media integration like FB, Instagram etc.
5 | CRM Integrations
B | Assumptions
1 | Estimates are high level and to be re-estimated in case of change in requirements/understanding/assumptions
2 | Website is developed in Drupal and hosted on Acquia cloud
3 | Client to Acquia cloud environment details
4 | Client to share drupal admin Backend and codebase access
5 | Client to share the details of any third party APIs integration
6 | The application is going to support the latest 4 browsers (chrome, Mozilla, safari and Edge) and 2 iOS and Android device
7 | UI/UX changes to be estimated separately
8 | QA testing is restricted to manual only
Note on A6: While estimating consider the following points in mind: - Technical complexity - Domain knowledge - Third party software dependency - Complexity of the software - Scalability of the Software - Security of software - Reusability of Software - Analyst and programmer capability - Experience of team in the application area - Experience of team with the programming language and computer - Use of tools and software engineering practices - Experience of team on Testing Software
Note on B34: Rework would follow review/ testing. Generally, rework efforts are estimated at 5-7% of total efforts
Note on B36: (Based on no. of builds)
Note on D7: Feasibility Study (FS) Time taken for Feasibility Study. This is applicable only if there is a feasibility study of the project is required Else enter the value 0 Estimates need to be put in the persondays .
Note on E7: Requirements Management (RM) following are the efforts should be considered while estimating for thr requirements: - Generation of the work product like SRS, RUD etc. - Rework effort - Verification effort i.e. time for requirements review - Planning and orientation effort Estimates need to be put in the persondays i.e. 2 personhours= .25 persondays 4 personhours= .5 persondays 8 personhours= 1 persondays
Note on F7: Design: following are the efforts should be considered while estimating for thr requirements: - Generation of the work product like HLD, LLD etc. - Rework effort - Verification effort i.e. time for Design review - Planning and orientation effort Estimates need to be put in the persondays i.e. 2 personhours= .25 persondays 4 personhours= .5 persondays 8 personhours= 1 persondays
Note on G7: Coding: following are the efforts should be considered while estimating for thr requirements: - Generation of the work product (code) - Rework effort - Verification effort i.e. time for code review - Planning and orientation effort Estimates need to be put in the persondays i.e. 2 personhours= .25 persondays 4 personhours= .5 persondays 8 personhours= 1 persondays
Note on I7: Testing: Following are the efforts should be considered while estimating for thr requirements: - Generation of the work product like writing test cases (SI, UAT etc) and executing test cases. - Rework effort - Verification effort i.e. time for test case review - Planning and orientation effort Estimates need to be put in the persondays i.e. 2 personhours= .25 persondays 4 personhours= .5 persondays 8 personhours= 1 persondays